## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Vikram | 2025-08-21 | OCR misreads Aadhaar number spacing | Sprint 1 | Vikram | Logical | Parsing fixed | 2025-08-21 | Closed | Root cause: regex for Aadhaar parsing
2 | Vikram | 2025-08-22 | Photo upload fails for >2MB images | Sprint 1 | Vikram | Logical | Fixed backend | 2025-08-22 | Open | Backend issue solved
3 | Vikram | 2025-08-28 | Tamper detection false positive for low-quality scan | Sprint 2 | Vikram | Logical | Investigated & fixed in backend | 2025-08-28 | Closed | Backend issue solved
4 | Vikram | 2025-08-29 | Supabase insert intermittently times out | Sprint 2 | Vikram | Maintainability | Issue recovered | 2025-08-29 | Open | Routing enhanced
5 | Vikram | 2025-09-04 | Redaction blurs face area accidentally | Sprint 3 | Vikram | Maintainability | Investigated & fixed in backend | 2025-09-04 | Closed | Backend modified
6 | Vikram | 2025-09-05 | Certificate PDF missing QR code | Sprint 3 | Vikram | User Interface | Routed successfully | 2025-09-05 | Open | Issue recovered
7 | Vikram | 2025-09-11 | OCR misreads Aadhaar number spacing | Sprint 4 | Vikram | Logical | Investigated & fixed in backend | 2025-09-11 | Closed | Root cause: regex for Aadhaar parsing
8 | Vikram | 2025-09-12 | Photo upload fails for >2MB images | Sprint 4 | Vikram | Maintainability | Storage improved | 2025-09-12 | Open | Backend issue solved
9 | Vikram | 2025-09-18 | Tamper detection false positive for low-quality scan | Sprint 5 | Vikram | Logical | Backend restarted | 2025-09-18 | Closed | Follow-up required
10 | Vikram | 2025-09-19 | Supabase insert intermittently times out | Sprint 5 | Vikram | Logical | App routed | 2025-09-19 | Open | Follow-up required
11 | Vikram | 2025-09-25 | Redaction blurs face area accidentally | Sprint 6 | Vikram | Logical | Investigated & fixed in backend | 2025-09-25 | Closed | Follow-up required
12 | Vikram | 2025-09-26 | Certificate generation | Sprint 6 | Vikram | Maintainability | Final testing | 2025-09-26 | closed | Model re-trained

## Sheet2
Logical
User Interface
Maintainability
Standards
Others